Code No: 220401.

Set No:

1

II B.Tech. II-Semester Supplementary Examinations, November 2003

MANAGEMENT SCIENCE

( Common to Electronics and Communications Engineering,

Electronics and Telematics  )

Time: 3 hours							Max.Marks:80

Answer any FIVE questions

All questions carry equal marks

---

1.	Distinguish between effectiveness and efficiency. Discuss the factors, which 	make an effective manager.

2.	What do you mean by strategy? Discuss the process of strategy formulation.

3.	Explain plant location and plant layout concepts with suitable illustrations.

4.	What are the different methods of training?

5.	What are the merits and demerits of centralized and decentralized buying?  For what type of situations and kinds of materials would you prefer centralization or decentralization of buying?

6.	Write short notes on:  (a) Branding   (b) Standardization  (c) sales promotion.

7.	A critical path activity is given below. The activity times are given besides each activity.

22

17

19

12

20

4

18

27

16

Mark the events according to Fulkerson’s Rule.

Determine the critical path and the critical path time.

(Contd…2)

Code No: 220401.				.. 2..				Set No: 1

8.	The particulars of cost and duration of a project is given below:

| Activity | Normal Cost Days Cost (Rs.) |  | Crash Cost Days Cost (Rs.) |  |
| --- | --- | --- | --- | --- |
| 1-2 | 3 | 500 | 2 | 1000 |
| 1-3 | 2 | 750 | 1 | 1500 |
| 1-4 | 6 | 1400 | 4 | 2600 |
| 2-4 | 5 | 1000 | 3 | 1800 |
| 2-5 | 7 | 1150 | 6 | 1450 |
| 3-4 | 2 | 800 | 2 | 800 |
| 4-5 | 4 | 1000 | 2 | 2400 |

a) Draw the network for normal cost and find critical path time, and cost of the

project.

b) Crash the critical path and compute the cost of the project.

~ ~ ~ ~

Code No: 220401.

Set No:

2

II B.Tech. II-Semester Supplementary Examinations, November 2003

MANAGEMENT SCIENCE

( Common to Electronics and Communications Engineering,

Electronics and Telematics  )

Time: 3 hours							Max.Marks:80

Answer any FIVE questions

All questions carry equal marks

---

1.	Define management and administration. Is there any conflict between these two terms? How will you resolve their conflict?

2.	Discuss strategies at different levels in a corporate enterprise.

3.	What do you understand by quality control? Explain its significance and 	techniques.

4.	What is selection? Outline the steps of selection.

5.	Write notes on:

a) Purchase requisition	b) Notice for inviting tenders

c) Comparative statement	d) Purchase order

6.	Write short notes on:  (a) safety stock.  (b)  Bin card   (c) Lead time

7.	A project has the following characteristics:

| Activity | Optimistic Time (days) | Pessimistic Time (days) | Most Likely Time (days) |
| --- | --- | --- | --- |
| 1-2 | 1 | 5 | 1.5 |
| 2-3 | 1 | 3 | 2 |
| 2-4 | 1 | 5 | 3 |
| 3-5 | 3 | 5 | 4 |
| 4-5 | 2 | 4 | 3 |
| 4-6 | 3 | 7 | 5 |
| 5-7 | 4 | 6 | 5 |
| 6-7 | 6 | 8 | 7 |
| 7-8 | 2 | 6 | 4 |
| 7-9 | 5 | 8 | 6 |
| 8-10 | 1 | 3 | 2 |
| 9-10 | 3 | 7 | 5 |

Construct a PERT network. Find the critical path and variance for each event. Find the project duration at 95% probability.

(Contd…2)

Code No: 220401.				.. 2..				Set No: 2

8.	List of activities for erecting a canteen in the factory is given below with other relevant details.  Job A must preceed all others while job E must follow all others. Apart from this, jobs can run concurrently.

_____________________________________________________________________

# Normal

Code     Job Description	    ---------------------------------------------- Crash cost (Rs)

Duration             Cost          Duration

(Days)                (Rs)            (Days) ____________________________________________________________

A	Lay foundations 		5	        3000	      4	             4000

and build walls

B	Tile roofing 			6	        1200	      2		2000

C 	Instal electricity		4                  1000              3		1800

D	Instal plumbing		5	         1200	      3		2000

# E	Connect services to finish	3	         1600	      3		1600

_____________________________________________________________________

- Draw the network and identify critical path.

- Crash the network fully to find out minimum duration.

- If indirect costs are Rs.300/day, determine the time-cost trade-off for the project.

~ ~ ~ ~

Code No: 220401.

Set No:

3

II B.Tech. II-Semester Supplementary Examinations, November 2003

MANAGEMENT SCIENCE

( Common to Electronics and Communications Engineering,

Electronics and Telematics  )

Time: 3 hours							Max.Marks:80

Answer any FIVE questions

All questions carry equal marks

---

1.	What are the essential characteristics of management? Is Management Science an exact one as in the case of Physics, Chemistry etc?  Explain.

2.	What is mission? What are the determinants of mission?

3.	Discuss the main techniques of statistical quality control.

4.	What is job evaluation? What are its advantages?

5. a)	Discuss the procedure usually adopted for the receipt and issue of items in a stores.

b)	Discuss the various types of records and registers to be maintained in stores.

6.	What is ‘Consumer orientation’?  Explain the important stages of developing suitable marketing process for:

(i) manufactured products and 	(ii) services.

7.	A Project consisting of 12 distinct activities is to be analysed by using PERT.

Draw the PERT network. Indicate the expected total slack for each activity and hence indicate the average critical path. With in how many days would you expect the project to be completed with 99% chances?

The following information is given (the time estimates are in days)

| ACTIVITY | PREDECESSOR ACTIVITY | OPTIMISTIC TIME (days) | NORMAL TIME (days) | PESSIMISTIC TIME (days) |
| --- | --- | --- | --- | --- |
| A | - | 2 | 2 | 2 |
| B | - | 1 | 3 | 7 |
| C | A | 4 | 7 | 8 |
| D | A | 3 | 5 | 7 |
| E | B | 2 | 6 | 9 |
| F | B | 5 | 9 | 11 |
| G | C,D | 3 | 6 | 8 |
| H | E | 2 | 6 | 9 |
| I | C,D | 3 | 5 | 8 |
| J | G,H | 1 | 3 | 4 |
| K | F | 4 | 8 | 11 |
| L | J,K | 2 | 5 | 7 |

(Contd…2)

Code No: 220401.				.. 2..				Set No: 3

8.	The following table gives the information about various activities of a project network.

| Activity | Normal duration (Days) | Normal Cost (Rs.) | Crash duration (Days) | Crash Cost (Rs.) |
| --- | --- | --- | --- | --- |
| 1-2 | 9 | 8000 | 7 | 10,000 |
| 1-3 | 5 | 5000 | 3 | 8,000 |
| 2-3 | 7 | 7000 | 5 | 8,600 |
| 2-4 | 8 | 6000 | 6 | 7,000 |
| 3-4 | 6 | 9000 | 4 | 11,400 |

The overhead costs are Rs.1300 per day.  Determine the optimum cost and duration of the project.

~ ~ ~ ~

Code No: 220401.

Set No:

4

II B.Tech. II-Semester Supplementary Examinations, November 2003

MANAGEMENT SCIENCE

( Common to Electronics and Communications Engineering,

Electronics and Telematics  )

Time: 3 hours							Max.Marks:80

Answer any FIVE questions

All questions carry equal marks

---

1.	Define Management. Explain the functions of management.

2.	What is SWOT analysis? How to develop strategic alternatives in the light of 	SWOT analysis?

3.	Explain the concept of SQC.  Explain how you can constract control charts for the 	variables.

4.	Define merit rating. Explain and evaluate any four methods of merit rating.

5.	Write short notes on:

a) Bin card 					b) Closed Vs open stores

c) Material transfer and material return note 	d) Stores ledger.

6.	Discuss the principles of ‘Motion Economy’ and explain how they are applicable to   	i) Manual operations

ii) Designing work at a work station.	  iii) Materials  handling.

7.	The following information is available about the various activities of a network.

| Activity | Normal duration (Days) | Normal Cost (Rs.) | Crash duration (Days) | Crash Cost (Rs.) |
| --- | --- | --- | --- | --- |
| 1-2 | 4 | 4000 | 3 | 7000 |
| 1-3 | 8 | 5000 | 7 | 8000 |
| 2-3 | 5 | 8000 | 3 | 10,000 |

Project overhead costs are at Rs.2000 per week.

Determine 	(i) direct cost duration relation ship.	(ii) Total cost duration relationship, also draw the least cost network.

(Contd…2)

Code No: 220401.				.. 2..				Set No: 4

8.	The following table indicates the sequence activities and the three time estimates. (a) Draw the network (b) Find the critical path (c) Find the expected project completion time and its standard deviation.

ACTIVITY     PRECEEDING         SUCCEEDING      	TIME ESTIMATES IN WEEK

ACTIVITY               ACTIVITY       -------------------------------------------------------

OPTIMISTIC         MOST       PESSIMISTIC

A		        -	                            C                   5                  7               15

B                        -                                D                   2                  3                4

C                        A                              E                    7                  9               17

D                       B                              F                     5                  6               13

E                        C                              -                     4                  5                12

F                         D                             -                     2                  4                 6

~ ~ ~ ~