Code No:220401

Set No.

1

# II B.Tech. II Semester Supplementary Examinations January,  2003

# MANAGEMENT SCIENCE

(Common to Electronics & Communication Engineering, Electronics & Telematics)

Time: 3 Hours							Max. Marks: 80

Answer any Five questions

All questions carry equal marks

---

1.  a)	Distinguish Administration and Management with illustrations.

- What are the social responsibilities of manager?

2.	What is environmental scanning.  Discuss its scope in corporate strategy.

3.	Discuss various functions of personnel management.

4.  a)	Distinguish batch and mass production with illustrative examples.

- Discuss role of materials management in industry.

5.	Discuss role of work study in improving productivity.  What are the barriers for introducing such study.  How management will take remedial steps to tide over the situation.

6.  a)	Distinguish PERT and CPM and their specific application area.

- Find critical path and duration of project for a project with following data.

EVENT			PREVIOUS			DAYS OF

NUMBER			NUMBER		       COMPLETION

12	11	3

10	4

9	12

11	8	2

6	3

10	7	8

9	8	2

7	3

5	4

8	6	2

4	8

7	3	36

6	4	2

5	4	3

3	2

4	2	2

3	2	4

2	1	4

Contd……2.

Code No:220401				:: 2 ::				Set No.1

7.	With an example illustrate mission, objectives, programmes and goals of any organization.

- Write short notes on any two

  - Managerial objectives

  - Merit rating

  - ABC analysis

@@@@@

Code No:220401

Set No.

2

# II B.Tech. II Semester Supplementary Examinations January,  2003

# MANAGEMENT SCIENCE

(Common to Electronics & Communication Engineering, Electronics & Telematics)

Time: 3 Hours							Max. Marks: 80

Answer any Five questions

All questions carry equal marks

---

1.	With help of organizational chart discuss various types of organisations.

2.	With an illustration discuss SWOT analysis and its importance in corporate strategy.

3.  a)	Why are human resources are considered to be critical and important asset of any organization

b)	Discuss procedure involved in merit rating and its significance in human resource management.

4.  a)	With illustration discuss ABC analysis and its necessity in industrial organization.

b)	Discuss  various procedures involved in purchase in purchasing right quality in right quantity at right time.

5.  a)	Define productivity. How can productivity be increased in an organization.

b)	Distinguish work study and method study mentioning their role in improving productivity.

6.	Determine critical path and path of variance for following data.

| EVENT | PREVIOUS EVENT | ta | tb | tc |
| --- | --- | --- | --- | --- |
| 8 | 7 | 20 | 30 | 40 |
|  | 6 | 15 | 20 | 35 |
|  | 5 | 8 | 12 | 15 |
| 7 | 4 | 30 | 35 | 50 |
|  | 3 | 3 | 7 | 12 |
| 6 | 3 | 40 | 45 | 65 |
|  | 2 | 25 | 35 | 50 |
| 5 | 2 | 55 | 70 | 95 |
| 4 | 1 | 10 | 20 | 35 |
| 3 | 1 | 5 | 15 | 25 |
| 2 | 1 | 10 | 15 | 30 |

7.  a)	Discuss role of statistical quality control in quality assurance.

b)	What is meant by time-cost option in PERT.  How can it effect critical path.

8.	Write short notes on any two      a)	Plant location for IT industry

b)     Marketing functions           c)	Job evaluation.

@@@@@

Code No:220401

Set No.

3

# II B.Tech. II Semester Supplementary Examinations January,  2003

# MANAGEMENT SCIENCE

(Common to Electronics & Communication Engineering, Electronics & Telematics)

Time: 3 Hours							Max. Marks: 80

Answer any Five questions

All questions carry equal marks

---

1.  a)	Distinguish formal and informal organization b)Discuss principles of organization

2.  a)	Discuss the scope of statistical quality control in industries.

b)	What is corporate planning.  Discuss steps involving in it.

3.  a)	Discuss scope of stores management in reducing cost of production.

b)	Discuss procedure involved in method study.

4.  	What is job evaluation?  Discuss various steps involved in job evaluation  will job evaluation techniques vary from organisation to organisation.

5.	Discuss functions of marketing management.  What type of marketing strategy is most suitable for educational institution.

6.	Find the path variance for following data.

EVENT			PREVIOUS			DAYS OF

NUMBER			NUMBER		       COMPLETION

12	11	3

10	4

9	12

11	8	2

6	3

10	7	8

9	8	2

7	3

5	4

8	6	2

4	9

7	3	35

6	4	2

5	4	3

3	3

2	2

4	2	2

3				      2				      4

2				      1				      3

1				      4

Contd……2.

Code No:220401				:: 2 ::				Set No.3

7.	Discuss various channels of distribution and with reasoning explain your choice for distribution of perishable products.

8.	Write short notes on any TWO

a)	Organisational span

b)	Environmental scanning

c)	Project crashing.

@@@@@

Code No:220401

Set No.

4

# II B.Tech. II Semester Supplementary Examinations January,  2003

# MANAGEMENT SCIENCE

(Common to Electronics & Communication Engineering, Electronics & Telematics)

Time: 3 Hours							Max. Marks: 80

Answer any Five questions

All questions carry equal marks

---

1.	Discuss critically functions of management with illustrations

2.	Classify plant layout and discuss merits, limitations and applications of different types of plant layout.

3.	Why is man power planning necessary in any organisation.  What are the steps involved in man power planning.

4.  a)	What are various inventory costs?  Derive equation for economic order quantity.  Mentioning assumptions.

b)	Discuss basic procedure involved in work study.  What is rating and how it is given in work study.

5.	Discuss various channels of distribution highlighting their merits and limitations.  What type of channel is most appropriate for continuing education in information technology.

6.  a)	Explain steps involved in project crashing.

b)	Discuss modern thought of management to suit globalization.

7.	With the following data construct network and determine path variance.  How does probability of completion is determined using this values.

| EVENT | PREVIOUS EVENT | ta | tb | tc |
| --- | --- | --- | --- | --- |
| 8 | 7 | 22 | 28 | 34 |
|  | 6 | 14 | 18 | 22 |
|  | 5 | 10 | 15 | 20 |
| 7 | 4 | 20 | 25 | 30 |
|  | 3 | 5 | 8 | 12 |
| 6 | 3 | 35 | 40 | 45 |
|  | 2 | 25 | 30 | 35 |
| 5 | 2 | 55 | 70 | 95 |
| 4 | 1 | 10 | 20 | 35 |
| 3 | 1 | 6 | 16 | 24 |
| 2 | 1 | 10 | 15 | 30 |

Contd……2.

Code No:220401				:: 2 ::				Set No.4

8.	Write short notes on any TWO.

a)	Managerial Objectives

b)	ABC Analysis

c)	SWOT Analysis

@@@@@