Code No.310855

OR

- III-B.Tech. I-Semester Supplementary Examinations, June 2003

MANAGEMENT SCIENCE

(Common to Chemical Engineering, Computer Science and Information Technology, Electronics and Instrumentation Engineering and Electronics and Control Engineering)

Time: 3 Hours							   Max. Marks: 70

Answer any FIVE questions

All questions carry equal marks.

---

1.a)	Distinguish between ‘Administration’ and ‘Management’.

b)	Explain the contribution of Taylor for the application of scientific principles in the field of Management.

2.a)	What are the basic managerial objectives and social responsibilities of Business?

b)	Draw an ‘Organisation Chart’ and explain its uses.

3.a)	What is a ‘strategy’?  How is it formulated?

b)	State and explain the implementation process of a strategy.

4.a)	Define ‘Plant Layout’ and what are its objectives?

b)	Distinguish between ‘Process Layout’ and ‘Product layout’.

c)	To what type of works each one is best suited.

5.a)	What are the broad areas to be covered by Human Resources Development Division in a big organization.

b)	Narrate the important functions of personnel Manager for Institutional Development.

6.a)	What do you understand by ’Method study’?

b)	Explain the basic procedure to be followed under ‘Method study.

c)	What are the objectives for applying ‘Method study’?

7.	Write short notes on:

a) Channels of Distribution

b) Statistical Quality Control

c) Project crashing.

Contd…2.

Code No.310855				:: 2 :: 					OR

8.	With the following data draw a network diagram and identify EST, EFT, LFT, LST and critical path.

| Activity | Event i-J | Duration (in weeks) | Preceeding Activities |
| --- | --- | --- | --- |
| A | 1-2 | 4 | - |
| B | 1-3 | 6 | - |
| C | 1-4 | 5 | - |
| D | 2-5 | 3 | A |
| E | 3-5 | 4 | B |
| F | 4-6 | 10 | C |
| G | 5-7 | 9 | D,E |
| H | 3-6 | 8 | B |
| I | 6-7 | 10 | H,F |

@@@@@