Code No.: 420109

Set No.

1

IV/IV B.Tech II-Semester Examination April, 2003

CONSTRUCTION MANAGEMENT AND PLANNING

(Civil Engineering)

Time: 3 hours							Max. Marks: 80

Answer any five questions

All questions carry equal marks

---

1.	Briefly explain ‘Construction Management’ and its relevance in government 	departments.

2.	Write a detailed note on tenders.

3.	Write a detailed note on PERT.

4.	The following are the activities of a project.

a) Draw the network diagram.

b) Find the project length.

c) Calculate total and free float for each activity.

| Activity | Duration(hours) |
| --- | --- |
| 1-2 | 1 |
| 2-3 | 3 |
| 2-4 | 3 |
| 3-5 | 4 |
| 4-5 | 2 |
| 4-6 | 5 |
| 4-7 | 9 |
| 5-7 | 4 |
| 6-7 | 2 |
| 7-8 | 2 |

5.	Write the concepts of material and equipment management.

6.	Explain about Accounting system and Book keeping.

7.	What do you mean by cost control?  What are its purposes?

8.	What is trade union?  What are its functions?  Write about Minimum Wage Act.

###

Code No.: 420109

Set No.

2

IV/IV B.Tech II-Semester Examination April, 2003

CONSTRUCTION MANAGEMENT AND PLANNING

(Civil Engineering)

Time: 3 hours							Max. Marks: 80

Answer any five questions

All questions carry equal marks

---

1.	Write a detailed note on contracts.

2.	Write a detailed note on tenders.

3.	Describe CPM in detail.

4.	The following are the activities of a project.

| Activity | Optimistic time (to) days | Most likely time(t2) days | Pebbimibitc time (tp) days |
| --- | --- | --- | --- |
| 1-2 | 2 | 5 | 14 |
| 1-3 | 3 | 12 | 21 |
| 2-4 | 5 | 14 | 17 |
| 3-4 | 2 | 5 | 8 |
| 3-5 | 6 | 15 | 30 |
| 4-5 | 1 | 4 | 7 |

- Draw the network diagram.

- Find the project length.

- Find the variance and standard deviation of project length.

5.	Discuss the utility and planning of resources for construction Industry.

6. a)	What are the objectives of quality control?

b)	Write a note on sampling and testing of materials.

7.	Discuss the cost and benificial management in construction projects.

8. a)	What are the different provisions  made in the Industrial Disputes Act to settle 	disputes in industries?

b)	Write the different types of labours.

###

Code No.: 420109

Set No.

3

IV/IV B.Tech II-Semester Examination April, 2003

CONSTRUCTION MANAGEMENT AND PLANNING

(Civil Engineering)

Time: 3 hours							Max. Marks: 80

Answer any five questions

All questions carry equal marks

---

1.	Write a detailed note on types of contract.

2.	Write a detailed note on tenders.

3. 	The following are the activities of a project

| Operation | Duration (days) | Is dependent only upon operation | Operation | Duration (days) | Is dependent only upon operation |
| --- | --- | --- | --- | --- | --- |
| A | 7 | - | E | 6 | C |
| B | 5 | A | F | 13 | B, C |
| C | 8 | A | G | 9 | D, E |
| D | 11 | B | H | 3 | D, F |

- Draw the network diagram.

- Find the project length.

- Calculate total and free float for each activity.

4.	The following are the activities of a project:

| Activity i-j | Optimistic To | Most likely TL | Pesimistic Tp |
| --- | --- | --- | --- |
| 1-2 | 1 | 1 | 7 |
| 1-3 | 1 | 4 | 7 |
| 1-4 | 2 | 2 | 8 |
| 2-5 | 1 | 1 | 1 |
| 3-5 | 2 | 5 | 14 |
| 4-6 | 2 | 5 | 8 |
| 5-6 | 3 | 6 | 15 |

- Draw the network diagram

- Find the project length.

- Find the variance and standard deviation of project length.

Contd…2

Code No. : 420109				.2.			Set No:3

5. a)	Write the basic concepts of equipment Management and Material Management.

b)	Explain inventory control.

6.	Write short notes on

i) 	Internal auditing

ii)	Profit and loss account

- Balance sheet

- Book keeping

7.	Briefly explain about budget, cost volume relationship, concept of valuation and 	cost of equity.

8.	What are the important features of Workmen’s Compensation Act and Industrial 	Disputes Act?

###

Code No.: 420109

Set No.

4

IV/IV B.Tech II-Semester Examination April, 2003

CONSTRUCTION MANAGEMENT AND PLANNING

(Civil Engineering)

Time: 3 hours							Max. Marks: 80

Answer any five questions

All questions carry equal marks

---

1.	Explain the various types of organizations involved in construction projects.

2.	Explain briefly the procedure of opening the tenders and acceptance of tenders.

3.a)	State the difference between CPM and PERT.

b)	Define :

i)	Total float

ii)	Free float

4.	The following are the activities of a project:

| Job Duration (days) |  |  |  |
| --- | --- | --- | --- |
| i - j | Optimistic | Most likely | Pessimistic |
| 1 2 | 3 | 6 | 15 |
| 1 6 | 2 | 5 | 14 |
| 2 3 | 6 | 12 | 30 |
| 2 4 | 2 | 5 | 8 |
| 3 5 | 5 | 11 | 17 |
| 4 5 | 3 | 6 | 15 |
| 6 7 | 3 | 9 | 27 |
| 5 8 | 1 | 4 | 7 |
| 7 8 | 4 | 19 | 28 |

- Draw the network diagram.

- Find the project length.

- Find the variance and standard deviation of project length.

5.	What are the essential requirements to be considered in the selection of materials, equipments and plants for a project?

6.	Write a detailed note on quality control in construction management.

7.	Describe fully the details of financial management.

8.	Describe briefly:

i)	Minimum Wages Act

ii)	Workman’s Compensation Act.

###